## Requirements Traceability
Project |  | Project Manager
Sawit The Last Chance |  | Perdylasta |  | Requirements Traceability Matrix
Date
2026-04-08
ID | Requirement Name | Requirement Description | Type of Requirement | Test Case | Status
FR-01 | Player memulai permainan | Main Menu System | UI Menu | TC-01 Start Game | Pending
FR-02 | Mengelola lahan | Farming System | Sistem Tanam & Panen | TC-02 Farming | Pending
FR-03 | Hitung hasil produksi | Production System | Kalkulasi hasil | TC-03 Production | Pending
FR-04 | Dampak lingkungan | Environment Simulation | Sistem cause-effect | TC-04 Environment | Pending
FR-05 | NPC dialog edukatif | NPC System | Dialog System | TC-05 NPC Interaction | Pending
FR-06 | Narasi berkembang | Story System | Story Progression | TC-06 Story Progress | Pending
FR-07 | Save & load progress | Save System | DataStore Roblox | TC-07 Save/Load | Pending
FR-08 | Inventory player | Inventory System | UI Inventory | TC-08 Inventory | Pending
FR-09 | Currency system | Economy System | Sistem uang | TC-09 Currency | Pending
FR-10 | Progression system | Leveling System | Unlock fitur | TC-10 Leveling | Pending
FR-11 | Reward/feedback | Reward System | Feedback engine | TC-11 Reward | Pending
FR-12 | UI navigasi | UI System | HUD & Menu | TC-12 UI | Pending
FR-13 | Status player | Player Status UI | HUD Status | TC-13 Status | Pending
FR-14 | Jalan di Roblox | Platform Integration | Roblox Engine | TC-14 Compatibility | Pending
FR-15 | Interaksi dasar | Control System | Movement & Action | TC-15 Control | Pending
NFR-01 | Performance | Game lancar | FPS stabil | TC-N01 Performance | Pending
NFR-02 | Usability | Mudah digunakan | User testing | TC-N02 Usability | Pending
NFR-03 | Reliability | Data tidak hilang | Save consistency | TC-N03 Reliability | Pending
NFR-04 | Availability | Bisa diakses kapan saja | Uptime server | TC-N04 Availability | Pending
NFR-05 | Compatibility | Mobile & PC | Multi-device test | TC-N05 Compatibility | Pending
NFR-06 | Security | Data aman | Access control | TC-N06 Security | Pending
NFR-07 | Scalability | Banyak player | Load test | TC-N07 Scalability | Pending
NFR-08 | Maintainability | Mudah dikembangkan | Struktur kode | TC-N08 Maintainability | Pending
NFR-09 | Efficiency | Resource optimal | CPU & Memory | TC-N09 Efficiency | Pending
NFR-10 | Portability | Hanya Roblox | Platform check | TC-N10 Portability | Pending
NFR-11 | Responsiveness | Respon cepat | < 2 detik | TC-N11 Response | Pending
NFR-12 | Integrity | Data akurat | Data validation | TC-N12 Integrity | Pending

## Sheet1
User Authentication | Enable secure login for users with unique credentials | Functional | Stakeholder Request | High | Unauthorized access, poor user adoption | In Progress | IT Team Lead | Users can log in and out securely | Test invalid login, password reset, and lockout scenarios | Improve platform security and user experience
Payment Integration | Implement payment gateway for seamless transactions | Functional | Market Analysis | High | Payment failures, loss of revenue | Not Started | Product Manager | Transactions are processed within 5 seconds | Test successful, failed, and duplicate payments | Enhance revenue stream and user convenience
Data Backup Mechanism | Implement daily automatic backups of user data | Non-functional | Compliance Requirement | Medium | Data loss during recovery, increased storage cost | Completed | DevOps Engineer | Daily backups are accessible and restorable | Test backup scheduling, accessibility, and data recovery | Ensure data integrity and disaster recovery